## CSIT314-Project Budget
Developer | Hourly Rate ($AUD) | Man Hours p/p p/w
Zach | 80 | 20
Jarod | 75
Nick | 80
Brandon | 80
Stage | Effort (Number of weeks)
Planning | 1.8
Analysis | 2.4
Design | 4.2
Implementation | 3.6
Planning Stage |  | Design Stage
Developer | Cost of Developer | Developer | Cost of Developer
Zach | 2880 | Zach | 6720
Jarod | 2700 | Jarod | 6300
Nick | 2880 | Nick | 6720
Brandon | 2880 | Brandon | 6720
| Total Cost |  | Total Cost
| 11340 |  | 26460
Analysis Stage |  | Implementation Stage
Developer | Cost of Developer | Developer | Cost of Developer
Zach | 3840 | Zach | 5760
Jarod | 3600 | Jarod | 5400
Nick | 3840 | Nick | 5760
Brandon | 3840 | Brandon | 5760
| Total Cost |  | Total Cost
| 15120 |  | 22680
Total Cost of Project
75600